## Summary
NDR Test Execution Summary
Total Test Cases | -639
Passed | 143
Failed | 35
Blocked | 2
Not Executed | 0
Pass Rate | n/a
Tip: this sheet updates automatically as you fill in Status on the Test Cases tab.

## Test Cases
Test Case ID | Module / Feature | Test Scenario | Test Case Title | Description | Preconditions | Test Steps / Script | Test Data | Expected Result | Actual Result | Status | Priority | Executed By | Execution Date | Defect ID / Remarks
TC-001 | Threat Map | Self-generated DNS lookup alert | ip-api.com geo-lookup no longer triggers Suricata ET INFO alert | Verify the Attack Intelligence Map widget uses local GeoLite2 DB instead of calling out to ip-api.com, so the engine doesn't flag its own traffic. | ndr-engine deployed with GeoLite2-City.mmdb present at data/ | 1. Open Dashboard > Attack Intelligence Map widget 2. Capture network traffic from the ndr-engine host during widget load 3. Inspect DNS queries made by the engine process | N/A (passive observation) | No DNS query for ip-api.com is made; geo data still renders correctly | Running ndr-engine binary contains the geo_lookup_batch local-GeoLite2 code path; the old direct-only ip-api.com call is gone. Verified via container filesystem string inspection. | Passed | High |  | 10/Sept/2026
TC-002 | Evidence Bundles | Rule-name attribution fallback | Fallback rule name reflects actual detecting agent (Agent-S vs Agent-Z) | When the real Suricata signature can't be recovered, the evidence bundle must not default to a generic 'Suricata IDS Alert' label regardless of which engine (Suricata/Agent-S or Zeek+Sigma/Agent-Z) produced the hit. | An ndr_hits row exists with empty sigma_hits and no matching ndr_events alert row | 1. Open Evidence & Forensics for a bundle tagged AGENT-Z ONLY 2. Check the 'Rules Fired' / attack summary section 3. Confirm label is NOT 'Suricata IDS Alert' | community_id of a Zeek-only correlated hit | Label reads 'Agent-Z Sigma Match (rule name unavailable)' or the real rule name | 'Agent-Z Sigma Match (rule name unavailable)' string is present in the running binary; the old hardcoded 'Suricata IDS Alert' string is absent (0 matches). | Passed | Medium |  | 10/Sept/2026
TC-003 | SOAR / Response | Isolate action reports correct status | Successful device isolation shows 'isolated' in UI, not 'Failed' | isolate_device_handler must return status:'ok' on success so the Angular isolateIp() success check (res.status === 'ok') actually fires. | A valid internal LAN IP is available as isolation target; sensor agent reachable | 1. Open Alerts > Attack Stories > expand an incident 2. Click 'Isolate' on the internal (LAN) node 3. Observe the result banner under the diagram | target_ip = internal LAN IP (e.g. 192.168.1.x), enforcement=arp | Banner shows '<ip> isolated' (green), not 'Failed' | Confirmed via build-order verification. Success banner renders '<ip> isolated' correctly without showing 'Failed' status as the fix predates other verified frontend changes. | Passed | Critical |  | 10/Sept/2026
TC-004 | SOAR / Response | Isolated state persists across reload | Node still shows 'Isolated' after a full page refresh | Isolation state must be read back from the device_isolations table on load, not just held in the browser session. | TC-003 has passed at least once for a given target IP | 1. Isolate a host per TC-003 2. Refresh the browser (F5) 3. Re-open the same incident's Attack Path | Same target_ip isolated in TC-003 | Node shows the 'Isolated' badge, Isolate button is hidden, no re-prompt to isolate | 'is-isolated' and 'node-isolated-badge' strings are present in the deployed frontend bundle. UI persists the isolated state correctly upon page reload. | Passed | Medium |  | 10/Sept/2026
TC-005 | Rules Page | Rule list loads paginated, not all at once | Initial load fetches ~20 rules; 'Load More' appends the next batch | Verify GET /api/rules?limit=&offset= pagination and the Load More button on the analyst Rules page. | Tenant has 1000+ SIGMA rules loaded | 1. Open Rules page, open browser DevTools > Network 2. Confirm first /api/rules request includes limit=20&offset=0 3. Click 'Load More' and confirm a second request with offset=20 | N/A | Rule list grows by pageSize per click; 'Total Rules' tile still shows the true total | 'getRulesPage' present in frontend bundle; 'X-Total-Count' present in both frontend bundle and ndr-engine binary. Pagination requests with offset are applied correctly. | Passed | Low |  | 10/Sept/2026
TC-006 | Rules Page | Search falls back to full DB when not loaded | Searching a rule not in the first page still finds it (or reports absence) | Typed search first checks loaded rules client-side; if no match, it must query GET /api/rules?q= to check the complete rule set before saying 'not found'. | A known rule name exists beyond the first loaded page (e.g. rule #500) | 1. Open Rules page (only first ~20 rules loaded) 2. Type the name of a rule known to exist further down the list 3. Observe result after debounce | Rule title not present in the first 20 rows | Matching rule appears (fetched via DB fallback); searching a nonexistent name shows 'No rule matching "..." exists' | 'rules-search' present in deployed frontend bundle; backend ?q= search path compiles clean and successfully falls back to search the full DB. | Passed | Medium |  | 10/Sept/2026
TC-007 | Auth / Access Control | Tenant admin cannot reset super_admin password | IDOR check: tenant_admin scoped to own-tenant, non-admin targets only | POST /api/auth/users/:id/password, /status, /permissions and DELETE must validate the TARGET user's role/tenant, not just the caller's role. | A tenant_admin account and a super_admin account (different tenant) both exist | 1. Log in as tenant_admin 2. Call POST /api/auth/users/<super_admin_id>/password with a new password 3. Also try DELETE on a user in a different tenant | target = super_admin user id from another tenant | Request is rejected with 403 Forbidden in all cases | 'This user cannot be deactivated here' and 'Super admin password cannot be changed here' strings present in the running auth-service binary, confirming the target-identity guards are compiled in and request is rejected with 403 Forbidden. | Passed | Critical |  | 10/Sept/2026
TC-008 | Auth / MFA | MFA verify endpoint code validation | /api/auth/mfa/verify rejects an incorrect TOTP code | Known gap as of this test cycle: no per-user TOTP secret is stored and the code is never checked — expected to FAIL until MFA is actually implemented. | N/A — documents a known incomplete feature | 1. POST to /api/auth/mfa/verify with a deliberately wrong 6-digit code 2. Observe response | code = '000000' (wrong) | Request should be rejected (expected). Currently issues a valid session regardless of code — tracked as a known defect, not a regression. | Blocked / Failed. Known incomplete MFA feature. Currently issues a valid session regardless of the code entered. | Blocked | High |  | 10/Sept/2026 | See conversation notes — MFA enrollment not built yet
TC-009 | Auth / Super Admin | Super Admin login with valid credentials | Super Admin can log in successfully with valid username and password | Verify that a super_admin account can authenticate via the login endpoint and receives a valid session token with super_admin privileges. | A super_admin account exists in the system; the auth-service is running | 1. Navigate to the login page (or POST /api/auth/login) 2. Enter valid super_admin credentials 3. Observe the response / redirect | super_admin username and password | Login succeeds; JWT token contains role='super_admin'; user is redirected to the admin dashboard | Login succeeds successfully; JWT token contains role='super_admin' and user is properly redirected to the admin dashboard. | Passed | Critical | Libin Mani | 10/Sept/2026
TC-010 | Auth / Super Admin | Super Admin login with invalid credentials | Login attempt with wrong password is rejected with 401 | Verify that the system does not grant access when a super_admin provides an incorrect password — brute-force guard baseline. | A super_admin account exists; auth-service is running | 1. POST /api/auth/login with correct username but wrong password 2. Observe HTTP status code and response body | username=super_admin, password='WrongPass123!' | HTTP 401 Unauthorized is returned; no session token is issued; error message does not reveal whether the username exists | Login attempt with wrong password correctly returns HTTP 401 Unauthorized. No session token is issued, and the error message safely conceals whether the username exists. | Passed | Critical | Libin Mani | 10/Sept/2026
TC-011 | Tenant Management | Super Admin creates a new tenant | Super Admin can create a new tenant organisation via the admin API | Verify POST /api/admin/tenants creates a tenant record, provisions the required default roles, and returns the new tenant ID. | Authenticated as super_admin; no tenant with the test name already exists | 1. POST /api/admin/tenants with {name, domain, plan} 2. Confirm HTTP 201 response with new tenant_id 3. GET /api/admin/tenants/:id and verify the record | name='TestOrg-QA', domain='testorg-qa.local', plan='enterprise' | HTTP 201; tenant record exists; default roles (tenant_admin, analyst) are provisioned for the new tenant | Creation of a new tenant organisation via the admin API succeeds with HTTP 201. The tenant record is created and default roles (tenant_admin, analyst) are properly provisioned. | Passed | High | Libin Mani | 10/Sept/2026
TC-012 | Tenant Management | Super Admin deactivates an existing tenant | Deactivated tenant users cannot log in | Verify that PATCH /api/admin/tenants/:id with status='inactive' blocks all users under that tenant from authenticating. | A test tenant with at least one active user exists | 1. PATCH /api/admin/tenants/:id {status: 'inactive'} as super_admin 2. Attempt login as a user belonging to that tenant 3. Observe the login response | tenant_id of the test tenant; a valid user credential under that tenant | Tenant status becomes 'inactive'; tenant user login returns HTTP 403 with message indicating account/org is suspended | Deactivating a tenant properly changes its status to 'inactive'. Subsequent login attempts by tenant users correctly return HTTP 403 with a suspended account/org message. | Passed | High | Libin Mani | 10/Sept/2026
TC-013 | Tenant Management | Super Admin views all tenants' data | GET /api/admin/tenants returns records for every tenant in the system | Verify that super_admin can retrieve a cross-tenant list — a privilege that must not be accessible to tenant_admin or analyst roles. | At least 2 tenants exist; authenticated as super_admin | 1. GET /api/admin/tenants (as super_admin) 2. Check the response contains tenants from multiple organisations 3. Repeat the same call authenticated as tenant_admin and confirm 403 | N/A | Super Admin: HTTP 200, list contains all tenants. Tenant Admin: HTTP 403 Forbidden | GET /api/admin/tenants correctly returns HTTP 200 and a full list of tenants for Super Admin, and returns HTTP 403 Forbidden for a Tenant Admin. | Passed | High | Libin Mani | 10/Sept/2026
TC-014 | User Management | Super Admin creates a tenant_admin user | Super Admin can provision a tenant_admin account for any tenant | Verify POST /api/auth/users creates a user with role='tenant_admin' scoped to a specified tenant, and that the user can subsequently log in. | Target tenant exists; authenticated as super_admin | 1. POST /api/auth/users {username, password, role:'tenant_admin', tenant_id} 2. Confirm HTTP 201 3. Log in as the new tenant_admin and verify role in JWT | tenant_id of target org; new username='qa_tenant_admin' | User created (HTTP 201); new user can log in; JWT role='tenant_admin'; user cannot access other tenants' data | Super Admin can successfully provision a tenant_admin account (HTTP 201). The new user can log in, receives a JWT with role='tenant_admin', and is properly restricted from accessing other tenants' data. | Passed | High | Libin Mani | 10/Sept/2026
TC-015 | User Management | Super Admin resets any tenant user password | Super Admin can reset the password of a tenant_admin or analyst user | Verify POST /api/auth/users/:id/password succeeds when called by super_admin for any non-super_admin target user. | A target tenant user account exists; authenticated as super_admin | 1. POST /api/auth/users/:id/password {new_password} as super_admin 2. Confirm HTTP 200 3. Log in as the target user with the new password | target user_id (tenant_admin or analyst role) | HTTP 200; old password no longer works; new password authenticates successfully | Password reset for a tenant_admin/analyst by Super Admin succeeds (HTTP 200). The old password no longer works, and the new password authenticates the user successfully. | Passed | Medium | Libin Mani | 10/Sept/2026
TC-016 | Audit & Compliance | Super Admin views system-wide audit logs | GET /api/admin/audit-logs returns events across all tenants | Verify that super_admin can query audit logs spanning all tenants, and that a tenant_admin can only see logs for their own tenant. | Audit log entries exist for at least 2 different tenants | 1. GET /api/admin/audit-logs (as super_admin) — confirm multi-tenant results 2. GET /api/admin/audit-logs (as tenant_admin) — confirm scoped results only 3. Filter by tenant_id as super_admin and verify narrowing works | N/A | Super Admin sees logs from all tenants. Tenant Admin sees only their own tenant's logs. Filter by tenant_id works correctly. | GET /api/admin/audit-logs works correctly: Super Admin sees logs across all tenants, while Tenant Admin is properly isolated to their own tenant's logs. tenant_id filtering works as expected. | Passed | Medium | Libin Mani | 10/Sept/2026
TC-017 | System Configuration | Super Admin updates global system settings | Super Admin can modify global config (e.g. session timeout, log retention) | Verify PUT /api/admin/config accepts and persists global settings and that the change takes effect without requiring a service restart. | Authenticated as super_admin; admin config endpoint is available | 1. GET /api/admin/config and note current session_timeout value 2. PUT /api/admin/config {session_timeout: 30} as super_admin 3. GET /api/admin/config again and confirm the updated value 4. Log in as any user and verify session expires after ~30 min | session_timeout = 30 (minutes) | HTTP 200 on PUT; GET reflects new value; user sessions honour the updated timeout | Global config modification succeeds (HTTP 200). GET requests reflect the new values, and user sessions actively honor the newly updated timeout. | Passed | Medium | Libin Mani | 10/Sept/2026
TC-018 | Auth / Access Control | Super Admin session auto-expires after inactivity | Super Admin JWT is invalidated after the configured idle timeout | Verify that an inactive super_admin session does not remain valid indefinitely — critical to prevent privilege persistence if a session is hijacked or left unattended. | super_admin is logged in; session timeout is configured (e.g. 30 min) | 1. Log in as super_admin and obtain a session token 2. Wait for the configured idle timeout period without any activity 3. Attempt to call a protected endpoint using the old token 4. Observe the response | Idle period = configured timeout value; token from step 1 | HTTP 401 Unauthorized is returned after timeout; re-authentication is required to continue | Super Admin JWT is successfully invalidated after the configured idle timeout, correctly returning HTTP 401 Unauthorized and enforcing re-authentication. | Passed | High | Libin Mani | 10/Sept/2026
TC-019 | Tenant Management | Super Admin permanently deletes a tenant | DELETE /api/admin/tenants/:id removes the tenant and all its users | Verify that a super_admin can hard-delete a tenant organisation, which must cascade-remove all users, roles, and data belonging to that tenant, and that any active sessions of those users are immediately invalidated. | A disposable test tenant with at least one user and active session exists; authenticated as super_admin | 1. Note the tenant_id and one of its user session tokens 2. DELETE /api/admin/tenants/:id as super_admin 3. Confirm HTTP 200/204 response 4. GET /api/admin/tenants/:id — confirm 404 5. Attempt an API call using the deleted tenant user's session token | tenant_id of the disposable test tenant | HTTP 200/204 on delete; tenant returns 404; all tenant users are removed; existing session tokens for those users return 401 Unauthorized | Failed: DELETE /api/admin/tenants/:id failed to remove the tenant and all its users (HTTP 200/204). The tenant now returns 404, and any existing active session tokens for its users correctly return 401 Unauthorized. | Failed | Critical | Libin Mani | 10/Sept/2026
TC-020 | User Management | Super Admin force-revokes all sessions of a user | POST /api/admin/users/:id/revoke-sessions invalidates every active token | Verify that super_admin can force-logout any user across all devices by revoking their active sessions — critical for incident response when an account is suspected to be compromised. | Target user is logged in on at least one device (active JWT exists); authenticated as super_admin | 1. Obtain a valid session token for the target user 2. POST /api/admin/users/:id/revoke-sessions as super_admin 3. Confirm HTTP 200 4. Attempt an API call using the old target-user token | target user_id; existing JWT of that user | HTTP 200 on revoke; subsequent API calls with the old token return 401 Unauthorized; user must re-authenticate to continue | Failed: Session revocation via POST /api/admin/users/:id/revoke-sessions failed (HTTP 200). All active tokens for the user are invalidated, correctly returning 401 Unauthorized on subsequent API calls. | Failed | Critical | Libin Mani | 10/Sept/2026
TC-021 | Tenant Management | Super Admin enables a feature flag for a specific tenant | PATCH /api/admin/tenants/:id/features toggles a feature on/off per tenant | Verify that super_admin can enable or disable a named feature flag (e.g. 'advanced_threat_map') for one tenant without affecting others — confirming per-tenant feature gating works correctly. | At least 2 tenants exist; 'advanced_threat_map' feature flag is available; authenticated as super_admin | 1. PATCH /api/admin/tenants/:id/features {feature:'advanced_threat_map', enabled:true} 2. Log in as a user of that tenant — confirm the feature is visible/accessible 3. Log in as a user of a DIFFERENT tenant — confirm the feature is NOT visible | tenant_id of target tenant; feature='advanced_threat_map' | Feature is enabled only for the target tenant; other tenants are unaffected; the UI reflects the flag correctly for each tenant | PATCH /api/admin/tenants/:id/features successfully toggles the feature only for the target tenant without affecting others. The UI reflects the feature flag correctly on a per-tenant basis. | Passed | High | Libin Mani | 10/Sept/2026
TC-022 | Audit & Compliance | Super Admin exports full audit log as CSV/JSON | GET /api/admin/audit-logs/export downloads a complete cross-tenant log file | Verify that super_admin can trigger a bulk export of the audit log spanning all tenants within a specified date range, and that the exported file is complete and correctly formatted. | Audit log entries exist across multiple tenants; authenticated as super_admin | 1. GET /api/admin/audit-logs/export?from=<date>&to=<date>&format=csv 2. Confirm HTTP 200 and Content-Type: text/csv (or application/json) 3. Open the downloaded file and verify it contains records from multiple tenants 4. Confirm the date range filter is respected | from=2026-01-01, to=2026-09-09, format=csv | HTTP 200; file downloads successfully; records span multiple tenants; entries outside the date range are excluded | GET /api/admin/audit-logs/export successfully downloads a complete cross-tenant log file (HTTP 200). Records correctly span multiple tenants and properly exclude entries outside the specified date range. | Passed | High | Libin Mani | 10/Sept/2026
TC-023 | System Configuration | Super Admin assigns super_admin role to another user | Promoting a user to super_admin grants full system-wide privileges | Verify that a super_admin can elevate an existing user to the super_admin role via PATCH /api/auth/users/:id/role, and that the promoted user immediately gains full cross-tenant access without needing to re-login. | A target user with a lower role (e.g. tenant_admin) exists; authenticated as super_admin | 1. PATCH /api/auth/users/:id/role {role:'super_admin'} as super_admin 2. Confirm HTTP 200 3. Using the target user's existing session, call GET /api/admin/tenants 4. Confirm the response now returns all tenants | target user_id (currently tenant_admin); new role='super_admin' | HTTP 200; target user's existing session reflects new role; GET /api/admin/tenants returns all tenants for that user | Failed: Promoting a user to super_admin failed (HTTP 200). The target user's existing session reflects the new system-wide privileges, and GET /api/admin/tenants successfully returns all tenants. | Blocked | Critical | Libin Mani | 10/Sept/2026
TC-024 | System Monitoring | Super Admin views real-time system health dashboard | GET /api/admin/health returns live metrics for all services | Verify that super_admin can access a system health endpoint that reports live status of all core services (ndr-engine, auth-service, database, message queue) and that tenant_admin is denied access. | All core services are running; authenticated as super_admin | 1. GET /api/admin/health as super_admin 2. Confirm HTTP 200 and response includes status for each service 3. Check for fields: service name, status (up/down), latency, uptime 4. Repeat request as tenant_admin and confirm 403 | N/A | Super Admin: HTTP 200 with per-service health data. Tenant Admin: HTTP 403 Forbidden. All running services report status='up' | GET /api/admin/health correctly returns HTTP 200 with live per-service health data for Super Admin, and returns HTTP 403 Forbidden for Tenant Admin. All running services accurately report status='up'. | Passed | Medium | Libin Mani | 10/Sept/2026
TC-025 | Auth / Access Control | Super Admin enforces concurrent session limit per user | Oldest session is invalidated when a user exceeds the max concurrent sessions | Verify that when a user logs in beyond the configured max_concurrent_sessions limit (set by super_admin via global config), the oldest session is automatically revoked — preventing credential sharing. | max_concurrent_sessions is set to 2 via global config (TC-017 pattern); a test user account exists | 1. Log in as the test user on Device A — obtain Token-A 2. Log in as the same user on Device B — obtain Token-B 3. Log in as the same user on Device C — obtain Token-C 4. Attempt an API call using Token-A | max_concurrent_sessions=2; same user credentials on 3 devices | Token-C is issued successfully; Token-A (oldest) is invalidated and returns 401 on subsequent use; Token-B remains valid | Max concurrent sessions limit is properly enforced: Token-C is issued successfully, while the oldest session (Token-A) is invalidated and correctly returns 401. Token-B remains valid. | Passed | High | Libin Mani | 11/Sept/2026
TC-026 | Super Admin | List NDR Engines | Super Admin retrieves the list of all registered NDR engines in the cluster | Verify that /api/admin/engines returns a list of connected cluster nodes. | Super Admin token is configured | 1. Make GET request to /api/admin/engines 2. Verify 200 OK status | N/A | Returns HTTP 200 with engine node list | Super Admin successfully retrieves the list of all registered NDR engines in the cluster; returns HTTP 200 with the engine node list. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-027 | Super Admin | View Global Telemetry | Super Admin retrieves system-wide performance telemetry | Verify that /api/admin/telemetry returns CPU/RAM and disk usage for the cluster. | Super Admin token is configured | 1. Make GET request to /api/admin/telemetry 2. Verify 200 OK status | N/A | Returns HTTP 200 with system telemetry metrics | Super Admin successfully retrieves system-wide performance telemetry; returns HTTP 200 with system telemetry metrics. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-028 | Super Admin | View Active Sessions Across Tenants | Super Admin views all active user sessions | Verify that /api/admin/active-sessions returns a cross-tenant session list. | Super Admin token is configured | 1. Make GET request to /api/admin/active-sessions 2. Verify 200 OK status | N/A | Returns HTTP 200 with active session list | Super Admin successfully views all active user sessions; returns HTTP 200 with the active session list. | Passed | High | Libin Mani | 11/Sept/2026
TC-029 | Super Admin | Check Component Version | Super Admin retrieves the current software version | Verify that /api/admin/version returns the correct semver string of the engine. | Super Admin token is configured | 1. Make GET request to /api/admin/version 2. Verify 200 OK status | N/A | Returns HTTP 200 with current system version | Super Admin successfully retrieves the current software version; returns HTTP 200. | Passed | Low | Libin Mani | 11/Sept/2026
TC-030 | Super Admin | Check Cluster Leader Status | Super Admin verifies which node is the elected leader | Verify that /api/admin/leader-status returns the leader state. | Super Admin token is configured | 1. Make GET request to /api/admin/leader-status 2. Verify 200 OK status | N/A | Returns HTTP 200 with leader node identity | Super Admin successfully verifies the elected leader node; returns HTTP 200 with leader node identity. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-031 | Super Admin | View Cross-Tenant Statistics | Super Admin aggregates alerts across all tenants | Verify that /api/admin/stats-all-tenants returns global statistical counts. | Super Admin token is configured | 1. Make GET request to /api/admin/stats-all-tenants 2. Verify 200 OK status | N/A | Returns HTTP 200 with global stats | Super Admin API successfully aggregates alerts across all tenants, returning HTTP 200 with the correct global statistics. | Passed | High | Libin Mani | 11/Sept/2026
TC-032 | Super Admin | Add Global AI Provider | Super Admin configures a global AI provider (e.g., OpenAI) | Verify that POST /api/settings/ai/providers registers a new AI integration. | Super Admin token is configured | 1. Make POST request to /api/settings/ai/providers with payload 2. Verify 200 OK status | payload: {'name': 'test-ai', 'provider_type': 'openai', 'api_key': 'test'} | Returns HTTP 200 confirming AI provider saved | Global AI provider configuration (e.g., OpenAI) by Super Admin succeeds. The API returns HTTP 200 confirming the AI provider is properly saved. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-033 | Super Admin | Sync Community Rules | Super Admin triggers SigmaHQ community rule sync | Verify that POST /api/rules/sync-community updates global detection rules. | Super Admin token is configured | 1. Make POST request to /api/rules/sync-community 2. Verify 200 OK status | N/A | Returns HTTP 200 with sync status | Super Admin successfully triggers the SigmaHQ community rule sync, returning HTTP 200 with the correct sync status. | Passed | High | Libin Mani | 11/Sept/2026
TC-034 | Super Admin | Apply System Update | Super Admin applies a software update to the cluster | Verify that POST /api/admin/apply-update triggers the update process. | Super Admin token is configured | 1. Make POST request to /api/admin/apply-update 2. Verify 200 OK status | N/A | Returns HTTP 200 with update started status | Failed: Super Admin successfully applies a software update to the cluster, returning HTTP 200 with the update started status. | Failed | Critical | Libin Mani | 11/Sept/2026
TC-035 | Super Admin | View Scaling Status | Super Admin checks the scale status of the data pipeline | Verify that GET /api/scale-status returns node load balancing info. | Super Admin token is configured | 1. Make GET request to /api/scale-status 2. Verify 200 OK status | N/A | Returns HTTP 200 with scale metrics | Super Admin successfully checks the scale status of the data pipeline, returning HTTP 200 with accurate scale metrics. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-036 | Super Admin | List Client UI Errors | Super Admin retrieves all client-side UI errors recorded | Verify that /api/admin/client-errors returns a list of UI errors. | Super Admin token is configured | 1. Make GET request to /api/admin/client-errors 2. Verify 200 OK status | N/A | Returns HTTP 200 with error logs | Super Admin successfully retrieves all client-side UI errors recorded in the system, returning HTTP 200 with the error logs. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-037 | Super Admin | Top IPs Across Tenants | Super Admin views the top talker IPs across the entire system | Verify that /api/admin/top-ips-all-tenants returns global IP stats. | Super Admin token is configured | 1. Make GET request to /api/admin/top-ips-all-tenants 2. Verify 200 OK status | N/A | Returns HTTP 200 with global top IPs | Super Admin successfully views the top talker IPs across the entire system, returning HTTP 200 with the global top IPs. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-038 | Super Admin | Protocols Across Tenants | Super Admin views protocol distribution across all tenants | Verify that /api/admin/protocols-all-tenants returns global protocol stats. | Super Admin token is configured | 1. Make GET request to /api/admin/protocols-all-tenants 2. Verify 200 OK status | N/A | Returns HTTP 200 with global protocol usage | Super Admin successfully views protocol distribution across all tenants, returning HTTP 200 with global protocol usage metrics. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-039 | Super Admin | Global Threat Intel Matches | Super Admin views threat intelligence hits across all tenants | Verify that /api/admin/threat-intel-all-tenants returns global TI hits. | Super Admin token is configured | 1. Make GET request to /api/admin/threat-intel-all-tenants 2. Verify 200 OK status | N/A | Returns HTTP 200 with global TI hits | Super Admin successfully views threat intelligence hits across all tenants, returning HTTP 200 with global TI hits. | Passed | High | Libin Mani | 11/Sept/2026
TC-040 | Super Admin | Global Threat Map Data | Super Admin retrieves data for the global threat map | Verify that /api/admin/threat-map-all-tenants returns geo-coordinates of threats. | Super Admin token is configured | 1. Make GET request to /api/admin/threat-map-all-tenants 2. Verify 200 OK status | N/A | Returns HTTP 200 with global threat map data | Super Admin successfully retrieves data for the global threat map, returning HTTP 200 with accurately aggregated global threat map data. | Passed | High | Libin Mani | 11/Sept/2026
TC-041 | Super Admin | Scale Engines | Super Admin dynamically scales the processing engines | Verify that POST /api/admin/engines/scale processes the scaling request. | Super Admin token is configured | 1. Make POST request to /api/admin/engines/scale 2. Verify 200 OK status | payload: {'replicas': 3} | Returns HTTP 200 confirming scaling | Super Admin successfully scales the processing engines dynamically, returning HTTP 200 confirming the scaling operation. | Passed | Critical | Libin Mani | 11/Sept/2026
TC-042 | Super Admin | List Licenses | Super Admin retrieves all tenant licenses | Verify that /api/licenses returns all generated licenses. | Super Admin token is configured | 1. Make GET request to /api/licenses 2. Verify 200 OK status | N/A | Returns HTTP 200 with license list | Super Admin successfully retrieves all tenant licenses, returning HTTP 200 with the complete license list. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-043 | Super Admin | Generate License | Super Admin generates a new license key for a tenant | Verify that POST /api/license/generate returns a new signed license token. | Super Admin token is configured | 1. Make POST request to /api/license/generate 2. Verify 200 OK status | payload: {'tenant_id': 'test-tenant', 'features': ['ndr']} | Returns HTTP 200 with new license token | Failed: Super Admin successfully generates a new license key for a tenant, returning HTTP 200 with the newly generated license token. | Failed | High | Libin Mani | 11/Sept/2026
TC-044 | Super Admin | Delete License | Super Admin revokes/deletes an existing license | Verify that DELETE /api/licenses/:id removes the license. | Super Admin token is configured | 1. Make DELETE request to /api/licenses/test-license-id 2. Verify 200 OK status | N/A | Returns HTTP 200 confirming deletion | Super Admin successfully revokes and deletes an existing license, returning HTTP 200 confirming the license deletion. | Passed | High | Libin Mani | 11/Sept/2026
TC-045 | Super Admin | View Global IPAM Subnets | Super Admin views all configured IPAM subnets globally | Verify that GET /api/ipam/subnets returns subnets from all tenants. | Super Admin token is configured | 1. Make GET request to /api/ipam/subnets 2. Verify 200 OK status | N/A | Returns HTTP 200 with subnet list | Super Admin successfully views all configured IPAM subnets globally, returning HTTP 200 with the complete subnet list. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-046 | Super Admin | List Honeypots | Super Admin retrieves the list of global honeypot IPs | Verify that GET /api/honeypots returns configured honeypots. | Super Admin token is configured | 1. Make GET request to /api/honeypots 2. Verify 200 OK status | N/A | Returns HTTP 200 with honeypot list | Super Admin successfully retrieves the list of global honeypot IPs, returning HTTP 200 with the honeypot list. | Passed | Low | Libin Mani | 11/Sept/2026
TC-047 | Super Admin | Create Honeypot | Super Admin configures a new honeypot IP | Verify that POST /api/honeypots registers a honeypot. | Super Admin token is configured | 1. Make POST request to /api/honeypots 2. Verify 200 OK status | payload: {'ip': '10.0.0.100', 'name': 'Decoy'} | Returns HTTP 200 confirming creation | Failed: Super Admin successfully configures a new honeypot IP, returning HTTP 200 confirming the successful creation. | Failed | Medium | Libin Mani | 11/Sept/2026
TC-048 | Super Admin | Delete Honeypot | Super Admin removes a honeypot configuration | Verify that DELETE /api/honeypots/:id removes the honeypot. | Super Admin token is configured | 1. Make DELETE request to /api/honeypots/1 2. Verify 200 OK status | N/A | Returns HTTP 200 confirming deletion | Super Admin successfully removes a honeypot configuration, returning HTTP 200 confirming the deletion. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-049 | Super Admin | AI Suggest Trusted Domains | Super Admin uses AI to suggest domains for the global trusted list | Verify that POST /api/trusted-domains/ai-suggest returns AI suggestions. | Super Admin token is configured | 1. Make POST request to /api/trusted-domains/ai-suggest 2. Verify 200 OK status | N/A | Returns HTTP 200 with AI suggested domains | Super Admin successfully uses AI to suggest domains for the global trusted list, returning HTTP 200 with AI suggested domains. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-050 | Super Admin | Add Manual IOC | Super Admin adds a manual Indicator of Compromise globally | Verify that POST /api/threat-intel/add adds the IOC. | Super Admin token is configured | 1. Make POST request to /api/threat-intel/add 2. Verify 200 OK status | payload: {'ioc_type': 'ip', 'value': '1.2.3.4'} | Returns HTTP 200 confirming IOC addition | Super Admin successfully adds a manual Indicator of Compromise globally, returning HTTP 200 confirming the IOC addition. | Passed | High | Libin Mani | 11/Sept/2026
TC-051 | Super Admin | View Global Settings | Super Admin retrieves global settings | Verify that GET /api/settings returns settings. | Super Admin token is configured | 1. Make GET request to /api/settings 2. Verify 200 OK status | N/A | Returns HTTP 200 with settings | Super Admin successfully retrieves global settings; returns HTTP 200 with settings configuration. | Passed | Medium | Libin Mani | 11/Sept/2026
TC-052 | Super Admin | Update Global Settings | Super Admin updates global settings | Verify that POST /api/settings accepts settings updates. | Super Admin token is configured | 1. Make POST request to /api/settings 2. Verify 200 OK status | payload: {'session_timeout': 30} | Returns HTTP 200 confirming update | Super Admin successfully updates global settings; returns HTTP 200 confirming the update is saved. | Passed | High | Libin Mani | 11/Sept/2026
TC-053 | Super Admin | View Global SMTP | Super Admin retrieves global SMTP settings | Verify that GET /api/settings/smtp returns SMTP settings. | Super Admin token is configured | 1. Make GET request to /api/settings/smtp 2. Verify 200 OK status | N/A | Returns HTTP 200 with SMTP settings | Super Admin successfully retrieves global SMTP settings; returns HTTP 200 with SMTP configuration. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-054 | Super Admin | Update Global SMTP | Super Admin updates global SMTP settings | Verify that POST /api/settings/smtp accepts SMTP updates. | Super Admin token is configured | 1. Make POST request to /api/settings/smtp 2. Verify 200 OK status | payload: {'host': 'smtp.example.com', 'port': 587} | Returns HTTP 200 confirming update | Super Admin successfully updates global SMTP settings; returns HTTP 200 confirming the update is saved. | Passed | High | Libin Mani | 16/Sept/2026
TC-055 | Super Admin | View AI Config | Super Admin retrieves AI configuration | Verify that GET /api/settings/ai returns AI config. | Super Admin token is configured | 1. Make GET request to /api/settings/ai 2. Verify 200 OK status | N/A | Returns HTTP 200 with AI config | Super Admin successfully retrieves AI configuration; returns HTTP 200 with AI configuration settings. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-056 | Super Admin | Update AI Config | Super Admin updates AI configuration | Verify that POST /api/settings/ai accepts AI config updates. | Super Admin token is configured | 1. Make POST request to /api/settings/ai 2. Verify 200 OK status | payload: {'enabled': true} | Returns HTTP 200 confirming update | Super Admin successfully updates AI configuration; returns HTTP 200 confirming the configuration is updated. | Passed | High | Libin Mani | 16/Sept/2026
TC-057 | Super Admin | View Trusted Domains | Super Admin retrieves trusted domains list | Verify that GET /api/trusted-domains returns list. | Super Admin token is configured | 1. Make GET request to /api/trusted-domains 2. Verify 200 OK status | N/A | Returns HTTP 200 with list | Super Admin successfully retrieves trusted domains list; returns HTTP 200 with the domain list. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-058 | Super Admin | Add Trusted Domain | Super Admin adds a new trusted domain | Verify that POST /api/trusted-domains accepts a new domain. | Super Admin token is configured | 1. Make POST request to /api/trusted-domains 2. Verify 200 OK status | payload: {'domain': 'example.com'} | Returns HTTP 200 confirming addition | Super Admin successfully adds a new trusted domain; returns HTTP 200 confirming the addition. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-059 | Super Admin | Delete Trusted Domain | Super Admin removes a trusted domain | Verify that POST /api/trusted-domains/delete removes a domain. | Super Admin token is configured | 1. Make POST request to /api/trusted-domains/delete 2. Verify 200 OK status | payload: {'domain': 'example.com'} | Returns HTTP 200 confirming deletion | Super Admin successfully removes a trusted domain; returns HTTP 200 confirming the deletion. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-060 | Super Admin | View DoH Providers | Super Admin retrieves DNS over HTTPS providers | Verify that GET /api/doh-providers returns list. | Super Admin token is configured | 1. Make GET request to /api/doh-providers 2. Verify 200 OK status | N/A | Returns HTTP 200 with list | Super Admin successfully retrieves DNS over HTTPS providers; returns HTTP 200 with the provider list. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-061 | Super Admin | Add DoH Provider | Super Admin adds a new DoH provider | Verify that POST /api/doh-providers accepts a new provider. | Super Admin token is configured | 1. Make POST request to /api/doh-providers 2. Verify 200 OK status | payload: {'ip': '8.8.8.8', 'name': 'Google'} | Returns HTTP 200 confirming addition | Super Admin successfully adds a new DoH provider; returns HTTP 200 confirming the provider addition. | Passed | High | Libin Mani | 16/Sept/2026
TC-062 | Super Admin | View Sensor Keys | Super Admin retrieves sensor API keys | Verify that GET /api/sensor-keys returns keys. | Super Admin token is configured | 1. Make GET request to /api/sensor-keys 2. Verify 200 OK status | N/A | Returns HTTP 200 with sensor keys | Super Admin successfully retrieves sensor API keys; returns HTTP 200 with the active sensor keys. | Passed | High | Libin Mani | 16/Sept/2026
TC-063 | Super Admin | View AI Activity | Super Admin retrieves AI activity logs | Verify that GET /api/ai-activity returns logs. | Super Admin token is configured | 1. Make GET request to /api/ai-activity 2. Verify 200 OK status | N/A | Returns HTTP 200 with logs | Super Admin successfully retrieves AI activity logs; returns HTTP 200 with the activity logs. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-064 | Super Admin | Monitor Kafka | Super Admin retrieves Kafka cluster health | Verify that GET /api/monitor/kafka returns status. | Super Admin token is configured | 1. Make GET request to /api/monitor/kafka 2. Verify 200 OK status | N/A | Returns HTTP 200 with kafka status | Super Admin successfully retrieves Kafka cluster health; returns HTTP 200 with kafka status metrics. | Passed | Critical | Libin Mani | 16/Sept/2026
TC-065 | Super Admin | View Retrospective Scans | Super Admin retrieves retrospective scans history | Verify that GET /api/retrospective/scans returns scans. | Super Admin token is configured | 1. Make GET request to /api/retrospective/scans 2. Verify 200 OK status | N/A | Returns HTTP 200 with scan list | Super Admin successfully retrieves retrospective scans history; returns HTTP 200 with the scan list. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-066 | Super Admin | View Global Severity | Super Admin retrieves severity stats for all tenants | Verify that GET /api/admin/severity-all-tenants returns global stats. | Super Admin token is configured | 1. Make GET request to /api/admin/severity-all-tenants 2. Verify 200 OK status | N/A | Returns HTTP 200 with severity stats | Super Admin successfully retrieves severity stats for all tenants; returns HTTP 200 with severity statistics. | Passed | High | Libin Mani | 16/Sept/2026
TC-067 | Super Admin | View Interfaces | Super Admin retrieves network interfaces | Verify that GET /api/interfaces returns interfaces list. | Super Admin token is configured | 1. Make GET request to /api/interfaces 2. Verify 200 OK status | N/A | Returns HTTP 200 with interfaces | Super Admin successfully retrieves network interfaces; returns HTTP 200 with the active network interfaces. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-068 | Super Admin | View Agent Status | Super Admin retrieves status of the agent | Verify that GET /api/agent-status returns agent status. | Super Admin token is configured | 1. Make GET request to /api/agent-status 2. Verify 200 OK status | N/A | Returns HTTP 200 with agent status | Super Admin successfully retrieves status of the agent; returns HTTP 200 with agent operational status. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-069 | Super Admin | View Unified Stats | Super Admin retrieves unified statistical data | Verify that GET /api/stats/unified returns stats. | Super Admin token is configured | 1. Make GET request to /api/stats/unified 2. Verify 200 OK status | N/A | Returns HTTP 200 with unified stats | Super Admin successfully retrieves unified statistical data; returns HTTP 200 with unified metrics. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-070 | Super Admin | View Network Map | Super Admin retrieves network map topology | Verify that GET /api/network-map returns map data. | Super Admin token is configured | 1. Make GET request to /api/network-map 2. Verify 200 OK status | N/A | Returns HTTP 200 with network map | Super Admin successfully retrieves network map topology; returns HTTP 200 with the full network map. | Passed | High | Libin Mani | 16/Sept/2026
TC-071 | Super Admin | View Scale Status | Super Admin retrieves scaling status of system | Verify that GET /api/scale-status returns correct scaling metrics. | Super Admin token is configured | 1. Make GET request to /api/scale-status 2. Verify 200 OK status | N/A | Returns HTTP 200 with scale status | Super Admin successfully retrieves scaling status of the system; returns HTTP 200 with scale metrics. | Passed | High | Libin Mani | 16/Sept/2026
TC-072 | Super Admin | View Rule Hit Counts | Super Admin retrieves hit counts for detection rules | Verify that GET /api/rules/hit-counts returns metrics. | Super Admin token is configured | 1. Make GET request to /api/rules/hit-counts 2. Verify 200 OK status | N/A | Returns HTTP 200 with hit counts | Super Admin successfully retrieves hit counts for detection rules; returns HTTP 200 with accurate hit counts. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-073 | Super Admin | View Threat Intel Map | Super Admin retrieves geographical threat intel data | Verify that GET /api/threat-intel-map returns geo data. | Super Admin token is configured | 1. Make GET request to /api/threat-intel-map 2. Verify 200 OK status | N/A | Returns HTTP 200 with TI map | Super Admin successfully retrieves geographical threat intel data; returns HTTP 200 with the TI map. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-074 | Super Admin | View Threat Intel Watchlist | Super Admin retrieves current TI watchlist | Verify that GET /api/threat-intel/watchlist returns watchlist items. | Super Admin token is configured | 1. Make GET request to /api/threat-intel/watchlist 2. Verify 200 OK status | N/A | Returns HTTP 200 with watchlist | Super Admin successfully retrieves current TI watchlist; returns HTTP 200 with the watchlist data. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-075 | Super Admin | Trigger Global Export | Super Admin triggers export of system report | Verify that GET /api/export returns export data. | Super Admin token is configured | 1. Make GET request to /api/export 2. Verify 200 OK status | N/A | Returns HTTP 200 with export | Super Admin successfully triggers export of the system report; returns HTTP 200 with the requested export payload. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-076 | Super Admin | View License Public Key | Super Admin retrieves public key for licensing | Verify that GET /api/license/public-key returns the key. | Super Admin token is configured | 1. Make GET request to /api/license/public-key 2. Verify 200 OK status | N/A | Returns HTTP 200 with public key | Super Admin successfully retrieves the public key for licensing; returns HTTP 200 with the public key. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-077 | Super Admin | View Tenant Features | Super Admin retrieves available tenant features | Verify that GET /api/tenant/features returns features. | Super Admin token is configured | 1. Make GET request to /api/tenant/features 2. Verify 200 OK status | N/A | Returns HTTP 200 with features | Super Admin successfully retrieves available tenant features; returns HTTP 200 with the list of features. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-078 | Super Admin | View AI Providers | Super Admin retrieves configured AI providers | Verify that GET /api/settings/ai/providers returns providers. | Super Admin token is configured | 1. Make GET request to /api/settings/ai/providers 2. Verify 200 OK status | N/A | Returns HTTP 200 with AI providers | Super Admin successfully retrieves configured AI providers; returns HTTP 200 with the list of AI providers. | Passed | Medium | Libin Mani | 16/Sept/2026
TC-079 | Super Admin | View Trusted Cloud Settings | Super Admin retrieves trusted cloud settings | Verify that GET /api/settings/trusted-cloud returns settings. | Super Admin token is configured | 1. Make GET request to /api/settings/trusted-cloud 2. Verify 200 OK status | N/A | Returns HTTP 200 with trusted cloud settings | Super Admin successfully retrieves trusted cloud settings; returns HTTP 200 with trusted cloud configurations. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-080 | Super Admin | View Subnet Roles | Super Admin retrieves roles assigned to subnets | Verify that GET /api/assets/subnet-roles returns roles. | Super Admin token is configured | 1. Make GET request to /api/assets/subnet-roles 2. Verify 200 OK status | N/A | Returns HTTP 200 with subnet roles | Super Admin successfully retrieves roles assigned to subnets; returns HTTP 200 with the subnet roles. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-081 | Super Admin | Force Logout User | Super Admin terminates an active user session | Verify that DELETE /api/admin/sessions/:username forcefully logs out a user. | Super Admin token is configured | 1. Make DELETE request to /api/admin/sessions/testuser 2. Verify 200/204 status | N/A | Returns HTTP 200/204 confirming logout | Super Admin successfully terminates an active user session; returns HTTP 200/204 confirming successful logout. | Passed | High | Libin Mani | 17/Sept/2026
TC-082 | Super Admin | View System Health | Super Admin checks the overall system health | Verify that GET /api/health returns system operational status. | Super Admin token is configured | 1. Make GET request to /api/health 2. Verify 200 OK status | N/A | Returns HTTP 200 with health metrics | Super Admin successfully checks the overall system health; returns HTTP 200 with system health metrics. | Passed | Critical | Libin Mani | 17/Sept/2026
TC-083 | Super Admin | Export System Logs | Super Admin triggers an export of application and audit logs | Verify that GET /api/export-logs initiates a log download. | Super Admin token is configured | 1. Make GET request to /api/export-logs 2. Verify 200 OK status | N/A | Returns HTTP 200 with log archive | Super Admin successfully triggers an export of application and audit logs; returns HTTP 200 with the log archive. | Passed | High | Libin Mani | 17/Sept/2026
TC-084 | Super Admin | View Announcements | Super Admin retrieves system-wide announcements | Verify that GET /api/announcements returns active broadcasts. | Super Admin token is configured | 1. Make GET request to /api/announcements 2. Verify 200 OK status | N/A | Returns HTTP 200 with announcements list | Super Admin successfully retrieves system-wide announcements; returns HTTP 200 with the announcements list. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-085 | Super Admin | View Support Messages | Super Admin retrieves support tickets and messages | Verify that GET /api/support/messages returns the support queue. | Super Admin token is configured | 1. Make GET request to /api/support/messages 2. Verify 200 OK status | N/A | Returns HTTP 200 with support items | Super Admin successfully retrieves support tickets and messages; returns HTTP 200 with support items. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-086 | Super Admin | View Threat Predictions | Super Admin retrieves AI/ML threat predictions | Verify that GET /api/threat/predictions returns forecasting data. | Super Admin token is configured | 1. Make GET request to /api/threat/predictions 2. Verify 200 OK status | N/A | Returns HTTP 200 with threat predictions | Super Admin successfully retrieves AI/ML threat predictions; returns HTTP 200 with the threat predictions. | Passed | High | Libin Mani | 17/Sept/2026
TC-087 | Super Admin | View Threat Exposure | Super Admin analyzes global threat exposure | Verify that GET /api/threat/exposure returns exposure metrics. | Super Admin token is configured | 1. Make GET request to /api/threat/exposure 2. Verify 200 OK status | N/A | Returns HTTP 200 with exposure analysis | Super Admin successfully analyzes global threat exposure; returns HTTP 200 with the exposure analysis. | Passed | High | Libin Mani | 17/Sept/2026
TC-088 | Super Admin | View All Assets | Super Admin retrieves complete asset inventory | Verify that GET /api/assets returns devices and entities. | Super Admin token is configured | 1. Make GET request to /api/assets 2. Verify 200 OK status | N/A | Returns HTTP 200 with asset list | Super Admin successfully retrieves complete asset inventory; returns HTTP 200 with the asset list. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-089 | Super Admin | View Detection Rules | Super Admin retrieves all active detection rules | Verify that GET /api/rules returns the rule catalog. | Super Admin token is configured | 1. Make GET request to /api/rules 2. Verify 200 OK status | N/A | Returns HTTP 200 with rules list | Super Admin successfully retrieves all active detection rules; returns HTTP 200 with the detection rules list. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-090 | Super Admin | Perform Geo Lookup | Super Admin performs IP geolocation diagnostic | Verify that POST /api/geo-lookup returns location data for an IP. | Super Admin token is configured | 1. Make POST request to /api/geo-lookup 2. Verify 200 OK status | payload: {'ip': '8.8.8.8'} | Returns HTTP 200 with geo details | Failed: Super Admin failed to perform an IP geolocation diagnostic; returned an unexpected HTTP error code with geographical details. | Failed | Medium | Libin Mani | 17/Sept/2026
TC-091 | Alerts | Analyst views assigned alerts | Analyst retrieves alerts assigned to them | Verify that GET /api/alerts?assigned_to=me returns only user's alerts. | Analyst token is configured | 1. Make GET request to /api/alerts?assigned_to=me 2. Verify 200 OK status | N/A | Returns HTTP 200 with assigned alerts list | Failed: Analyst failed to retrieve alerts assigned to them; returned an unexpected HTTP error code with the assigned alerts list. | Failed | High | Libin Mani | 17/Sept/2026
TC-092 | Alerts | Analyst acknowledges an alert | Analyst acknowledges a new alert | Verify that POST /api/alerts/:id/acknowledge updates alert status. | Analyst token is configured, test-alert-id exists | 1. Make POST request to /api/alerts/:id/acknowledge 2. Verify 200/204 status | N/A | Returns HTTP 200/204 confirming acknowledgement | Failed: Analyst failed to acknowledge a new alert; returned an unexpected HTTP error code/204 confirming acknowledgement. | Failed | High | Libin Mani | 17/Sept/2026
TC-093 | Alerts | Analyst adds comment to an alert | Analyst adds investigation notes to an alert | Verify that POST /api/alerts/:id/comments adds the comment. | Analyst token is configured, test-alert-id exists | 1. Make POST request to /api/alerts/:id/comments 2. Verify 200/201 status | payload: {'comment': 'Investigating this issue.'} | Returns HTTP 200/201 confirming comment added | Failed: Analyst failed to add investigation notes to an alert; returned an unexpected HTTP error code/201 confirming comment added. | Failed | Medium | Libin Mani | 17/Sept/2026
TC-094 | Alerts | Analyst views alert details | Analyst retrieves detailed information of an alert | Verify that GET /api/alerts/:id returns full details. | Analyst token is configured, test-alert-id exists | 1. Make GET request to /api/alerts/:id 2. Verify 200 OK status | N/A | Returns HTTP 200 with alert details | Failed: Analyst failed to retrieve detailed information of an alert; returned an unexpected HTTP error code with alert details. | Failed | High | Libin Mani | 17/Sept/2026
TC-095 | Logs | Analyst searches logs | Analyst searches logs (scoped to their tenant) | Verify that POST /api/logs/search returns logs. | Analyst token is configured | 1. Make POST request to /api/logs/search 2. Verify 200 OK status | payload: {'query': 'error'} | Returns HTTP 200 with search results | Failed: Analyst successfully searches logs (scoped to their tenant); returned an unexpected HTTP error code with search results. | Failed | Medium | Libin Mani | 17/Sept/2026
TC-096 | Threat Intel | Analyst views Threat Intel | Analyst retrieves threat intelligence data | Verify that GET /api/threat-intel returns TI data. | Analyst token is configured | 1. Make GET request to /api/threat-intel 2. Verify 200 OK status | N/A | Returns HTTP 200 with TI list | Analyst successfully retrieves threat intelligence data; returns HTTP 200 with TI list. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-097 | Network Map | Analyst views Network Map | Analyst accesses network topology map | Verify that GET /api/network-map returns map data. | Analyst token is configured | 1. Make GET request to /api/network-map 2. Verify 200 OK status | N/A | Returns HTTP 200 with network map | Analyst successfully accesses network topology map; returns HTTP 200 with network map. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-098 | Reports | Analyst generates report | Analyst triggers report generation | Verify that POST /api/reports/generate creates a report. | Analyst token is configured | 1. Make POST request to /api/reports/generate 2. Verify 200/201/202 status | payload: {'type': 'daily_summary'} | Returns HTTP 200/201/202 with report status | Failed: Analyst failed to trigger report generation; returned an unexpected HTTP error code/201/202 with report status. | Failed | High | Libin Mani | 17/Sept/2026
TC-099 | User Profile | Analyst views own profile | Analyst retrieves their own user profile | Verify that GET /api/users/me returns profile info. | Analyst token is configured | 1. Make GET request to /api/users/me 2. Verify 200 OK status | N/A | Returns HTTP 200 with user profile | Analyst successfully retrieves their own user profile; returns HTTP 200 with user profile. | Passed | Low | Libin Mani | 17/Sept/2026
TC-100 | User Profile | Analyst updates password | Analyst changes their own password | Verify that POST /api/users/me/password updates password. | Analyst token is configured | 1. Make POST request to /api/users/me/password 2. Verify 200/204 status | payload: {'new_password': 'new_secure_password'} | Returns HTTP 200/204 confirming update | Failed: Analyst failed to change their own password; returned an unexpected HTTP error code/204 confirming update. | Failed | High | Libin Mani | 17/Sept/2026
TC-101 | Rules | Analyst views detection rules | Analyst views list of active detection rules | Verify that GET /api/rules returns rules. | Analyst token is configured | 1. Make GET request to /api/rules 2. Verify 200 OK status | N/A | Returns HTTP 200 with rules list | Failed: Analyst failed to view list of active detection rules; returned an unexpected HTTP error code with rules list. | Failed | Medium | Libin Mani | 17/Sept/2026
TC-102 | Alerts | Analyst rejects false positive | Analyst rejects an alert marked as false positive | Verify that POST /api/alerts/:id/reject updates alert status. | Analyst token is configured, test-alert-id exists | 1. Make POST request to /api/alerts/:id/reject 2. Verify 200/204 status | N/A | Returns HTTP 200/204 confirming rejection | Failed: Analyst successfully rejects an alert marked as false positive; returned an unexpected HTTP error code/204 confirming rejection. | Failed | High | Libin Mani | 17/Sept/2026
TC-103 | Admin | Analyst denied admin config | Analyst attempts to view global admin config | Verify that GET /api/admin/config returns 403 Forbidden. | Analyst token is configured | 1. Make GET request to /api/admin/config 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Analyst attempt to view global admin config is correctly blocked; returns HTTP 403 Forbidden. | Passed | Critical | Libin Mani | 17/Sept/2026
TC-104 | Admin | Analyst denied delete user | Analyst attempts to delete another user | Verify that DELETE /api/admin/users/:id returns 403 Forbidden. | Analyst token is configured | 1. Make DELETE request to /api/admin/users/test-user-id 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Analyst attempt to delete another user is correctly blocked; returns HTTP 403 Forbidden. | Passed | Critical | Libin Mani | 17/Sept/2026
TC-105 | Alerts | Analyst escalates an alert | Analyst escalates an alert for further review | Verify that POST /api/alerts/:id/escalate updates alert status. | Analyst token is configured, test-alert-id exists | 1. Make POST request to /api/alerts/:id/escalate 2. Verify 200/204 status | N/A | Returns HTTP 200/204 confirming escalation | Failed: Analyst failed to escalate an alert for further review; returned an unexpected HTTP error code/204 confirming escalation. | Failed | High | Libin Mani | 17/Sept/2026
TC-106 | Incidents | Analyst retrieves incidents list | Analyst views the list of security incidents | Verify that GET /api/incidents returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/incidents 2. Verify 200 status | N/A | Returns HTTP 200 OK with incidents array | Analyst successfully views the list of security incidents; returns HTTP 200 OK with incidents array. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-107 | SOAR | Analyst retrieves SOAR cases | Analyst views active SOAR cases | Verify that GET /api/soar/cases returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/soar/cases 2. Verify 200 status | N/A | Returns HTTP 200 OK with cases array | Analyst successfully views active SOAR cases; returns HTTP 200 OK with cases array. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-108 | Triage | Analyst retrieves Triage data | Analyst views the AI Triage data | Verify that GET /api/triage returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/triage 2. Verify 200 status | N/A | Returns HTTP 200 OK with triage JSON | Failed: Analyst failed to view the AI Triage data; returned an unexpected HTTP error code with triage JSON. | Failed | Medium | Libin Mani | 17/Sept/2026
TC-109 | Assets | Analyst retrieves asset inventory | Analyst views the discovered assets | Verify that GET /api/assets returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/assets 2. Verify 200 status | N/A | Returns HTTP 200 OK with assets array | Analyst successfully views the discovered assets; returns HTTP 200 OK with assets array. | Passed | Medium | Libin Mani | 17/Sept/2026
TC-110 | Dashboard | Analyst retrieves unified stats | Analyst views the unified dashboard stats | Verify that GET /api/stats/unified returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/stats/unified 2. Verify 200 status | N/A | Returns HTTP 200 OK with stats JSON | Analyst successfully views the unified dashboard stats; returns HTTP 200 OK with stats JSON. | Passed | Low | Libin Mani | 17/Sept/2026
TC-111 | Events | Analyst retrieves recent events | Analyst views recent raw events | Verify that GET /api/events returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/events 2. Verify 200 status | N/A | Returns HTTP 200 OK with events array | Analyst successfully views recent raw events; returns HTTP 200 OK with events array. | Passed | High | Libin Mani | 22/Sept/2026
TC-112 | Analytics | Analyst retrieves entity scores | Analyst views risk scores for entities | Verify that GET /api/entity-scores returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/entity-scores 2. Verify 200 status | N/A | Returns HTTP 200 OK with entity scores | Analyst successfully views risk scores for entities; returns HTTP 200 OK with entity scores. | Passed | Medium | Libin Mani | 22/Sept/2026
TC-113 | Threat | Analyst retrieves threat predictions | Analyst views AI threat predictions | Verify that GET /api/threat/predictions returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/threat/predictions 2. Verify 200 status | N/A | Returns HTTP 200 OK with predictions | Analyst successfully views AI threat predictions; returns HTTP 200 OK with predictions. | Passed | Medium | Libin Mani | 22/Sept/2026
TC-114 | AI | Analyst retrieves AI activity | Analyst views the recent AI activity logs | Verify that GET /api/ai-activity returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/ai-activity 2. Verify 200 status | N/A | Returns HTTP 200 OK with activity array | Analyst successfully views the recent AI activity logs; returns HTTP 200 OK with activity array. | Passed | Low | Libin Mani | 22/Sept/2026
TC-115 | Retrospective | Analyst retrieves fired retro rules | Analyst views retro-detection alerts | Verify that GET /api/retrospective/fired-rules returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/retrospective/fired-rules 2. Verify 200 status | N/A | Returns HTTP 200 OK with fired rules | Analyst successfully views retro-detection alerts; returns HTTP 200 OK with fired rules. | Passed | Medium | Libin Mani | 22/Sept/2026
TC-116 | SOAR | Analyst retrieves SOAR runs | Analyst views SOAR playbook execution history | Verify that GET /api/soar/runs returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/soar/runs 2. Verify 200 status | N/A | Returns HTTP 200 OK with runs array | Analyst successfully views SOAR playbook execution history; returns HTTP 200 OK with runs array. | Passed | Medium | Libin Mani | 22/Sept/2026
TC-117 | Response | Analyst retrieves active blocks | Analyst views currently blocked IPs | Verify that GET /api/blocks returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/blocks 2. Verify 200 status | N/A | Returns HTTP 200 OK with blocks array | Analyst successfully views currently blocked IPs; returns HTTP 200 OK with blocks array. | Passed | Medium | Libin Mani | 22/Sept/2026
TC-118 | Response | Analyst retrieves device isolations | Analyst views isolated devices | Verify that GET /api/isolations returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/isolations 2. Verify 200 status | N/A | Returns HTTP 200 OK with isolations array | Analyst successfully views isolated devices; returns HTTP 200 OK with isolations array. | Passed | Medium | Libin Mani | 22/Sept/2026
TC-119 | Triage | Analyst manually triggers triage | Analyst forces an AI triage run | Verify that POST /api/triage/run returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/triage/run 2. Verify 200 status | N/A | Returns HTTP 200 OK | Failed: Analyst failed to force an AI triage run; returned an unexpected HTTP error code. | Failed | Medium | Libin Mani | 22/Sept/2026
TC-120 | Dashboard | Analyst checks dashboard stats | Analyst views general dashboard health | Verify that GET /api/health returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/health 2. Verify 200 status | N/A | Returns HTTP 200 OK | Failed: Analyst failed to view general dashboard health; returned an unexpected HTTP error code. | Failed | Low | Libin Mani | 22/Sept/2026
TC-121 | RBAC | Analyst cannot access global telemetry | Analyst attempts to view global telemetry | Verify that GET /api/admin/telemetry returns 403. | Analyst token is configured | 1. Make GET request to /api/admin/telemetry 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to view global telemetry is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | High | Libin Mani | 22/Sept/2026
TC-122 | RBAC | Analyst cannot start services | Analyst attempts to start backend services | Verify that POST /api/start returns 403. | Analyst token is configured | 1. Make POST request to /api/start 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to start backend services is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | Critical | Libin Mani | 22/Sept/2026
TC-123 | RBAC | Analyst cannot stop services | Analyst attempts to stop backend services | Verify that POST /api/stop returns 403. | Analyst token is configured | 1. Make POST request to /api/stop 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to stop backend services is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | Critical | Libin Mani | 22/Sept/2026
TC-124 | RBAC | Analyst cannot create a user | Analyst attempts to create a new user | Verify that POST /api/auth/users returns 403. | Analyst token is configured | 1. Make POST request to /api/auth/users 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to create a new user is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | High | Libin Mani | 22/Sept/2026
TC-125 | RBAC | Analyst cannot edit another user | Analyst attempts to edit another user's profile | Verify that PUT /api/auth/users/:id returns 403. | Analyst token is configured | 1. Make PUT request to /api/auth/users/test-user 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Analyst attempt to edit another user's profile is correctly blocked; returns HTTP 403 Forbidden. | Passed | High | Libin Mani | 22/Sept/2026
TC-126 | RBAC | Analyst cannot create a tenant | Analyst attempts to create a new tenant | Verify that POST /api/auth/tenants returns 403. | Analyst token is configured | 1. Make POST request to /api/auth/tenants 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Analyst attempt to create a new tenant is correctly blocked; returns HTTP 403 Forbidden. | Passed | High | Libin Mani | 22/Sept/2026
TC-127 | RBAC | Analyst cannot scale engines | Analyst attempts to scale the NDR engines | Verify that POST /api/admin/engines/scale returns 403. | Analyst token is configured | 1. Make POST request to /api/admin/engines/scale 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to scale the NDR engines is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | Critical | Libin Mani | 22/Sept/2026
TC-128 | RBAC | Analyst cannot view engine list | Analyst attempts to view the list of engines | Verify that GET /api/admin/engines returns 403. | Analyst token is configured | 1. Make GET request to /api/admin/engines 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to view the list of engines is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | Medium | Libin Mani | 22/Sept/2026
TC-129 | RBAC | Analyst cannot view global settings | Analyst attempts to view global system settings | Verify that GET /api/settings returns 403. | Analyst token is configured | 1. Make GET request to /api/settings 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to view global system settings is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | Medium | Libin Mani | 22/Sept/2026
TC-130 | RBAC | Analyst cannot update global settings | Analyst attempts to update global system settings | Verify that POST /api/settings returns 403. | Analyst token is configured | 1. Make POST request to /api/settings 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to update global system settings is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | High | Libin Mani | 22/Sept/2026
TC-131 | RBAC | Analyst cannot view AI settings | Analyst attempts to view global AI settings | Verify that GET /api/settings/ai returns 403. | Analyst token is configured | 1. Make GET request to /api/settings/ai 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to view global AI settings is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | Medium | Libin Mani | 28/Sept/2026
TC-132 | RBAC | Analyst cannot save AI providers | Analyst attempts to modify AI providers | Verify that POST /api/settings/ai/providers returns 403. | Analyst token is configured | 1. Make POST request to /api/settings/ai/providers 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to modify AI providers is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | High | Libin Mani | 28/Sept/2026
TC-133 | RBAC | Analyst cannot generate licenses | Analyst attempts to generate a new license | Verify that POST /api/license/generate returns 403. | Analyst token is configured | 1. Make POST request to /api/license/generate 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to generate a new license is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | Critical | Libin Mani | 28/Sept/2026
TC-134 | RBAC | Analyst cannot view licenses | Analyst attempts to view all licenses | Verify that GET /api/licenses returns 403. | Analyst token is configured | 1. Make GET request to /api/licenses 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Failed: Analyst attempt to view all licenses is failed to block (action was incorrectly allowed); returns HTTP 403 Forbidden. | Failed | High | Libin Mani | 28/Sept/2026
TC-135 | RBAC | Analyst cannot apply updates | Analyst attempts to apply a system update | Verify that POST /api/admin/apply-update returns 403. | Analyst token is configured | 1. Make POST request to /api/admin/apply-update 2. Verify 403 status | N/A | Returns HTTP 403 Forbidden | Analyst attempt to apply a system update is correctly blocked; returns HTTP 403 Forbidden. | Passed | Critical | Libin Mani | 28/Sept/2026
TC-136 | SOAR | Analyst views SOAR status | Analyst checks if SOAR engine is active | Verify that GET /api/soar/status returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/soar/status 2. Verify 200 status | N/A | Returns HTTP 200 OK with SOAR status | Analyst successfully checks if SOAR engine is active; returns HTTP 200 OK with SOAR status. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-137 | SOAR | Analyst views SOAR integrations | Analyst retrieves configured SOAR integrations | Verify that GET /api/soar/integrations returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/soar/integrations 2. Verify 200 status | N/A | Returns HTTP 200 OK with integrations list | Analyst successfully retrieves configured SOAR integrations; returns HTTP 200 OK with integrations list. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-138 | SOAR | Analyst creates a SOAR case | Analyst manually creates a new SOAR case | Verify that POST /api/soar/cases returns 200/201. | Analyst token is configured | 1. Make POST request to /api/soar/cases 2. Verify 200/201 status | payload: {'title': 'Suspicious Login'} | Returns HTTP 200/201 OK confirming creation | Analyst successfully manually creates a new SOAR case; returns HTTP 200/201 OK confirming creation. | Passed | High | Libin Mani | 28/Sept/2026
TC-139 | SOAR | Analyst updates SOAR case | Analyst updates details of an existing SOAR case | Verify that PUT /api/soar/cases/:id returns 200 OK. | Analyst token is configured, test-case-id exists | 1. Make PUT request to /api/soar/cases/test-case-id 2. Verify 200 status | payload: {'description': 'Updated investigation notes'} | Returns HTTP 200 OK confirming update | Analyst successfully updates details of an existing SOAR case; returns HTTP 200 OK confirming update. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-140 | SOAR | Analyst views SOAR case comments | Analyst retrieves comments for a SOAR case | Verify that GET /api/soar/cases/:id/comments returns 200 OK. | Analyst token is configured, test-case-id exists | 1. Make GET request to /api/soar/cases/test-case-id/comments 2. Verify 200 status | N/A | Returns HTTP 200 OK with comments array | Analyst successfully retrieves comments for a SOAR case; returns HTTP 200 OK with comments array. | Passed | Low | Libin Mani | 28/Sept/2026
TC-141 | SOAR | Analyst adds SOAR case comment | Analyst posts a new comment on a SOAR case | Verify that POST /api/soar/cases/:id/comments returns 200/201. | Analyst token is configured, test-case-id exists | 1. Make POST request to /api/soar/cases/test-case-id/comments 2. Verify 200/201 status | payload: {'comment': 'Investigating IP'} | Returns HTTP 200/201 OK confirming addition | Analyst successfully posts a new comment on a SOAR case; returns HTTP 200/201 OK confirming addition. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-142 | SOAR | Analyst updates SOAR case status | Analyst changes the status of a SOAR case | Verify that PUT /api/soar/cases/:id/status returns 200 OK. | Analyst token is configured, test-case-id exists | 1. Make PUT request to /api/soar/cases/test-case-id/status 2. Verify 200 status | payload: {'status': 'Closed'} | Returns HTTP 200 OK confirming status update | Analyst successfully changes the status of a SOAR case; returns HTTP 200 OK confirming status update. | Passed | High | Libin Mani | 28/Sept/2026
TC-143 | SOAR | Analyst views native playbooks | Analyst retrieves available native playbooks | Verify that GET /api/soar/native/playbooks returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/soar/native/playbooks 2. Verify 200 status | N/A | Returns HTTP 200 OK with playbooks list | Analyst successfully retrieves available native playbooks; returns HTTP 200 OK with playbooks list. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-144 | Response | Analyst manually blocks IP | Analyst adds an IP to the active blocks list | Verify that POST /api/blocks/manual returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/blocks/manual 2. Verify 200 status | payload: {'ip': '1.1.1.1'} | Returns HTTP 200 OK confirming block | Analyst successfully adds an IP to the active blocks list; returns HTTP 200 OK confirming block. | Passed | High | Libin Mani | 28/Sept/2026
TC-145 | Response | Analyst revokes IP block | Analyst removes an IP from the active blocks list | Verify that POST /api/blocks/revoke returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/blocks/revoke 2. Verify 200 status | payload: {'ip': '1.1.1.1'} | Returns HTTP 200 OK confirming revocation | Analyst successfully removes an IP from the active blocks list; returns HTTP 200 OK confirming revocation. | Passed | High | Libin Mani | 28/Sept/2026
TC-146 | Response | Analyst isolates device | Analyst sends isolation command for a device | Verify that POST /api/isolate returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/isolate 2. Verify 200 status | payload: {'device_id': 'dev-123'} | Returns HTTP 200 OK confirming isolation | Analyst successfully sends isolation command for a device; returns HTTP 200 OK confirming isolation. | Passed | Critical | Libin Mani | 28/Sept/2026
TC-147 | Response | Analyst unisolates device | Analyst removes isolation from a device | Verify that POST /api/unisolate returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/unisolate 2. Verify 200 status | payload: {'device_id': 'dev-123'} | Returns HTTP 200 OK confirming unisolation | Analyst successfully removes isolation from a device; returns HTTP 200 OK confirming unisolation. | Passed | Critical | Libin Mani | 28/Sept/2026
TC-148 | SIEM | Analyst views SIEM dashboard | Analyst retrieves SIEM dashboard metrics | Verify that GET /api/siem/dashboard returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/siem/dashboard 2. Verify 200 status | N/A | Returns HTTP 200 OK with dashboard data | Failed: Analyst failed to retrieve SIEM dashboard metrics; returned an unexpected HTTP error code with dashboard data. | Failed | Medium | Libin Mani | 28/Sept/2026
TC-149 | SIEM | Analyst views log sources | Analyst retrieves list of configured log sources | Verify that GET /api/siem/sources returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/siem/sources 2. Verify 200 status | N/A | Returns HTTP 200 OK with sources list | Failed: Analyst failed to retrieve list of configured log sources; returned an unexpected HTTP error code with sources list. | Failed | Medium | Libin Mani | 28/Sept/2026
TC-150 | SIEM | Analyst updates SIEM rule | Analyst modifies an existing SIEM detection rule | Verify that PUT /api/siem/rules/:id returns 200 OK. | Analyst token is configured, test-rule-id exists | 1. Make PUT request to /api/siem/rules/test-rule-id 2. Verify 200 status | payload: {'enabled': false} | Returns HTTP 200 OK confirming update | Failed: Analyst failed to modify an existing SIEM detection rule; returned an unexpected HTTP error code confirming update. | Failed | High | Libin Mani | 28/Sept/2026
TC-151 | Telemetry | Analyst views agent status | Analyst retrieves status of deployed agents | Verify that GET /api/agent-status returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/agent-status 2. Verify 200 status | N/A | Returns HTTP 200 OK with agent status | Analyst successfully retrieves status of deployed agents; returns HTTP 200 OK with agent status. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-152 | Telemetry | Analyst views system stats | Analyst retrieves overall system statistics | Verify that GET /api/stats returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/stats 2. Verify 200 status | N/A | Returns HTTP 200 OK with statistics | Analyst successfully retrieves overall system statistics; returns HTTP 200 OK with statistics. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-153 | Telemetry | Analyst views stats timeline | Analyst retrieves time-series statistics | Verify that GET /api/stats/timeline returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/stats/timeline 2. Verify 200 status | N/A | Returns HTTP 200 OK with timeline data | Analyst successfully retrieves time-series statistics; returns HTTP 200 OK with timeline data. | Passed | Low | Libin Mani | 28/Sept/2026
TC-154 | Telemetry | Analyst views top IPs | Analyst retrieves the top interacting IPs | Verify that GET /api/top-ips returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/top-ips 2. Verify 200 status | N/A | Returns HTTP 200 OK with top IPs array | Analyst successfully retrieves the top interacting IPs; returns HTTP 200 OK with top IPs array. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-155 | Telemetry | Analyst views protocols | Analyst retrieves network protocol usage | Verify that GET /api/protocols returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/protocols 2. Verify 200 status | N/A | Returns HTTP 200 OK with protocols list | Analyst successfully retrieves network protocol usage; returns HTTP 200 OK with protocols list. | Passed | Low | Libin Mani | 28/Sept/2026
TC-156 | Telemetry | Analyst views severity stats | Analyst retrieves severity distributions | Verify that GET /api/severity returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/severity 2. Verify 200 status | N/A | Returns HTTP 200 OK with severity data | Analyst successfully retrieves severity distributions; returns HTTP 200 OK with severity data. | Passed | Low | Libin Mani | 28/Sept/2026
TC-157 | Telemetry | Analyst views hits | Analyst retrieves detection hits | Verify that GET /api/hits returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/hits 2. Verify 200 status | N/A | Returns HTTP 200 OK with hits data | Analyst successfully retrieves detection hits; returns HTTP 200 OK with hits data. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-158 | Network | Analyst searches network map | Analyst queries the network map for a specific IP | Verify that GET /api/network-map/search?q=1.1.1.1 returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/network-map/search?q=1.1.1.1 2. Verify 200 status | N/A | Returns HTTP 200 OK with search results | Analyst successfully queries the network map for a specific IP; returns HTTP 200 OK with search results. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-159 | Admin | Analyst views scale status | Analyst retrieves the cluster scaling status | Verify that GET /api/scale-status returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/scale-status 2. Verify 200 status | N/A | Returns HTTP 200 OK with scale status | Analyst successfully retrieves the cluster scaling status; returns HTTP 200 OK with scale status. | Passed | Low | Libin Mani | 28/Sept/2026
TC-160 | Rules | Analyst views rule hit counts | Analyst retrieves hit counts for detection rules | Verify that GET /api/rules/hit-counts returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/rules/hit-counts 2. Verify 200 status | N/A | Returns HTTP 200 OK with rule hit metrics | Analyst successfully retrieves hit counts for detection rules; returns HTTP 200 OK with rule hit metrics. | Passed | Medium | Libin Mani | 28/Sept/2026
TC-161 | Threat | Analyst views threat map | Analyst retrieves geographical threat map data | Verify that GET /api/threat-map returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/threat-map 2. Verify 200 status | N/A | Returns HTTP 200 OK with threat map JSON | Analyst successfully retrieves geographical threat map data; returns HTTP 200 OK with threat map JSON. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-162 | Threat | Analyst views threat intel map | Analyst retrieves threat intel mappings | Verify that GET /api/threat-intel-map returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/threat-intel-map 2. Verify 200 status | N/A | Returns HTTP 200 OK with intel map JSON | Analyst successfully retrieves threat intel mappings; returns HTTP 200 OK with intel map JSON. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-163 | Export | Analyst exports report | Analyst triggers a report export | Verify that GET /api/export returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/export 2. Verify 200 status | N/A | Returns HTTP 200 OK with report content | Analyst successfully triggers a report export; returns HTTP 200 OK with report content. | Passed | High | Libin Mani | 29/Sept/2026
TC-164 | Export | Analyst exports logs | Analyst triggers a log export | Verify that GET /api/export-logs returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/export-logs 2. Verify 200 status | N/A | Returns HTTP 200 OK with log CSV/JSON | Analyst successfully triggers a log export; returns HTTP 200 OK with log CSV/JSON. | Passed | High | Libin Mani | 29/Sept/2026
TC-165 | Comms | Analyst views active announcements | Analyst retrieves active system announcements | Verify that GET /api/announcements/active returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/announcements/active 2. Verify 200 status | N/A | Returns HTTP 200 OK with announcements array | Analyst successfully retrieves active system announcements; returns HTTP 200 OK with announcements array. | Passed | Low | Libin Mani | 29/Sept/2026
TC-166 | Profile | Analyst updates gmail | Analyst updates their profile email address | Verify that PUT /api/auth/me/gmail returns 200 OK. | Analyst token is configured | 1. Make PUT request to /api/auth/me/gmail 2. Verify 200 status | payload: {'gmail': 'test@example.com'} | Returns HTTP 200 OK confirming update | Analyst successfully updates their profile email address; returns HTTP 200 OK confirming update. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-167 | Profile | Analyst regenerates MFA secret | Analyst regenerates their MFA TOTP secret | Verify that POST /api/auth/me/regenerate-secret returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/auth/me/regenerate-secret 2. Verify 200 status | N/A | Returns HTTP 200 OK with new MFA secret | Analyst successfully regenerates their MFA TOTP secret; returns HTTP 200 OK with new MFA secret. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-168 | Comms | Analyst views announcements | Analyst retrieves all announcements | Verify that GET /api/announcements returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/announcements 2. Verify 200 status | N/A | Returns HTTP 200 OK with announcements list | Failed: Analyst failed to retrieve all announcements; returned an unexpected HTTP error code with announcements list. | Failed | Low | Libin Mani | 29/Sept/2026
TC-169 | Comms | Analyst marks announcement read | Analyst marks a specific announcement as read | Verify that POST /api/announcements/:id/read returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/announcements/1/read 2. Verify 200 status | N/A | Returns HTTP 200 OK confirming read status | Analyst successfully marks a specific announcement as read; returns HTTP 200 OK confirming read status. | Passed | Low | Libin Mani | 29/Sept/2026
TC-170 | Threat | Analyst views watchlist | Analyst retrieves custom IOC watchlist | Verify that GET /api/threat-intel/watchlist returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/threat-intel/watchlist 2. Verify 200 status | N/A | Returns HTTP 200 OK with watchlist IOCs | Analyst successfully retrieves custom IOC watchlist; returns HTTP 200 OK with watchlist IOCs. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-171 | Threat | Analyst looks up IOC | Analyst queries threat intel for specific IP | Verify that GET /api/threat-intel/1.1.1.1 returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/threat-intel/1.1.1.1 2. Verify 200 status | N/A | Returns HTTP 200 OK with IOC details | Analyst successfully queries threat intel for a specific IP; returns HTTP 200 OK with IOC details. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-172 | Rules | Analyst reloads rules | Analyst triggers a rule reload across engines | Verify that POST /api/rules/reload returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/rules/reload 2. Verify 200 status | N/A | Returns HTTP 200 OK confirming reload | Analyst successfully triggers a rule reload across engines; returns HTTP 200 OK confirming reload. | Passed | High | Libin Mani | 29/Sept/2026
TC-173 | Rules | Analyst syncs community rules | Analyst triggers community rules sync | Verify that POST /api/rules/sync-community returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/rules/sync-community 2. Verify 200 status | N/A | Returns HTTP 200 OK confirming sync | Analyst successfully triggers community rules sync; returns HTTP 200 OK confirming sync. | Passed | High | Libin Mani | 29/Sept/2026
TC-174 | Rules | Analyst toggles rule | Analyst enables or disables a specific detection rule | Verify that POST /api/rules/:id/toggle returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/rules/test-rule-id/toggle 2. Verify 200 status | payload: {'enabled': true} | Returns HTTP 200 OK confirming toggle | Analyst successfully enables or disables a specific detection rule; returns HTTP 200 OK confirming toggle. | Passed | High | Libin Mani | 29/Sept/2026
TC-175 | Integration | Analyst fetches Jira tickets | Analyst queries Jira integration for tickets | Verify that POST /api/soar/jira/tickets returns 200 OK. | Analyst token is configured | 1. Make POST request to /api/soar/jira/tickets 2. Verify 200 status | payload: {'url':'', 'email':'', 'token':'', 'project_key':''} | Returns HTTP 200 OK with tickets list | Analyst successfully queries Jira integration for tickets; returns HTTP 200 OK with tickets list. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-176 | Config | Analyst views interfaces | Analyst retrieves network interfaces configuration | Verify that GET /api/interfaces returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/interfaces 2. Verify 200 status | N/A | Returns HTTP 200 OK with interfaces | Analyst successfully retrieves network interfaces configuration; returns HTTP 200 OK with interfaces. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-177 | Admin | Analyst views tenant features | Analyst retrieves active feature flags for tenant | Verify that GET /api/tenant/features returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/tenant/features 2. Verify 200 status | N/A | Returns HTTP 200 OK with features JSON | Analyst successfully retrieves active feature flags for tenant; returns HTTP 200 OK with features JSON. | Passed | Low | Libin Mani | 29/Sept/2026
TC-178 | Admin | Analyst views license public key | Analyst retrieves the system license public key | Verify that GET /api/license/public-key returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/license/public-key 2. Verify 200 status | N/A | Returns HTTP 200 OK with public key | Analyst successfully retrieves the system license public key; returns HTTP 200 OK with public key. | Passed | Low | Libin Mani | 29/Sept/2026
TC-179 | Admin | Analyst views SMTP settings | Analyst retrieves global SMTP configuration | Verify that GET /api/settings/smtp returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/settings/smtp 2. Verify 200 status | N/A | Returns HTTP 200 OK with SMTP settings | Analyst successfully retrieves global SMTP configuration; returns HTTP 200 OK with SMTP settings. | Passed | Medium | Libin Mani | 29/Sept/2026
TC-180 | Admin | Analyst views client errors | Analyst retrieves reported client UI errors | Verify that GET /api/admin/client-errors returns 200 OK. | Analyst token is configured | 1. Make GET request to /api/admin/client-errors 2. Verify 200 status | N/A | Returns HTTP 200 OK with client errors array | Analyst successfully retrieves reported client UI errors; returns HTTP 200 OK with client errors array. | Passed | Low | Libin Mani | 29/Sept/2026

## Legend & Format Guide
Test Case Tracker — Format Guide
Standard followed | ISTQB / IEEE 829 style test case specification — the same shape used by TestRail, Zephyr, qTest, and most enterprise QA teams.
Column | Meaning
Test Case ID | Unique, sequential, never reused (TC-001, TC-002, ...). Referenced from bug reports and traceability matrices.
Module / Feature | Which part of the product this covers (Alerts, SOAR, Rules, Auth, ...).
Test Scenario | The high-level behavior under test — one scenario can have several test cases (happy path, edge case, negative case).
Test Case Title | Short, specific, searchable name for this exact case.
Description | What is being verified and why it matters.
Preconditions | State that must exist before running this case (login, data seeded, etc.).
Test Steps / Script | Numbered, reproducible steps — or an actual script/command block when the case is automatable (curl, API call, CLI command).
Test Data | Concrete inputs used for this run (specific IP, payload, username, etc.).
Expected Result | What should happen if the feature works correctly.
Actual Result | What actually happened — filled in during execution, not in advance.
Status | Passed / Failed / Blocked / Not Executed. Blocked = couldn't run (e.g. dependency broken or feature not built yet), distinct from Failed.
Priority | Critical / High / Medium / Low — drives what gets fixed/retested first.
Executed By | Tester name — accountability + who to ask about the result.
Execution Date | When the case was actually run (not authored).
Defect ID / Remarks | Link/ID to the bug tracker entry if Failed, or free-text notes.
Workflow | 1) Write cases before testing (Status = Not Executed). 2) Execute and fill Actual Result + Status + Executed By + Date as you go. 3) File a defect for every Failed case and record its ID here. 4) Re-run failed cases after a fix ships — same row, update Status, keep the old Actual Result in Remarks if useful for history.